## Dapper Status 17 Nov 2005
Prorities	Status Indicators:
Essential	On track, all OK
High	Behind schedule, but will catch up
Medium	Blocked or needs management input
Low

Prio.	Stat.	Name	Assign	Status Update: 17 November 2005
infinity
High	Approved	reducing-duplication	adconrad	reducing-duplication: ongoing effort, currently beginning to focus on rebuilding everything against the One True openssl (0.9.8)
Medium	Drafting	usplash-initramfs	adconrad	initramfs/usplash-*: fixing vga16fb and syslinux to both run at 6x0, pushing changes to BenC to get the kernel to use update-initramfs in its postinst, most other initramfs stuff will be started in the next week or two, when Keybuk releases his "lock".
Medium	Approved	splash-down	adconrad	No update given.
Medium	Approved	initramfs-updates	adconrad	nitramfs stuff will be started in the next week or two, when Keybuk releases his "lock".
Low	Braindump	thinclient-usplash	adconrad	No update given.
General		General	infinity	misc-blocked: linux-restricted-modules waiting on Xorg to build (which is waiting on a new glibc from jbailey) before I bump us to new ATI drivers and fiddle with new Xorg and /lib/firmware paths. misc-nextweek: PHP security updates on my plate, and of course, more effort on the merge and bug triage fray. Buildd admin can taking a lot of time but hasn't been TOO painful this week.
Meeting:				Further meeting between infinity and mdz to discuss l-r-m and installer
BenC
High	Pending Approval	testing-server-hardware	ben-collins	To follow after 2.6.15 is completely installed and buildable.
Medium	Drafting	ubuntu-server-kernel	ben-collins	To follow after 2.6.15 is completely installed and buildable.
Medium	Approved	preventing-hardware-support-regr...	ben-collins	To follow after 2.6.15 is completely installed and buildable.
General			BenC	Got 2.6.15 into dapper, Working on getting powerpc64 buildable, No real showstoppers right now. Server configs to be started next week.
doko
Medium	Approved	toolchain-roadmap	doko	toolchain packages updated to current versions, not final releases. libstdc++ allocator changes start after flight-1, ia32-libs will start loosing packages next week (with glibc)
General		General	doko	java-updates: not yet started. others: no progress This week: - snycs - preparing libstdc++ allocator change - experimental gij/gcj-4.1 builds Next week: - libstdc++ allocator changes, toolchain bug trial- java to native code infrastructure for libjava packages some help next week for the libstdc++ allocator changes would be nice. Allocator changes requires renaming about 40 libs in main. rebuilding depending package etc. infinity and dholbach have offered to help out with this. Mithrandir asked doko to do the ooo-amd64 changes (to build native packages). It was agreed to wait until after the allocator change.
Meeting:				Further meeting between doko, JaneW and mdz to discuss dividing and managing workload
iwj/Diziet
High	Approved	automated-testing	ijackson	just started discussion in debian-policy about package test interface. That will go on for a week or two at least and then I hope it'll be settled. So not much coding yet.
General		General	iwj	default-applications-firefox: I'm working on the firefox merge-of-doom now. Not really blocking on anything but my computer but it's very tedious and slow. thinclient-local-devices: Still in drafting, blocking on design being done. developer-documentation: Not started. package-dependency-fix: Low priority, not started.Also on my list is Steve Alexander's request for some help with launchpad ssl client authentication. Which I haven't touched yet either. Plan for next week is to finish the damn firefox merge and then get on to Steve's ssl client thing, while being quite aggressive in participating in the automated-testing debian-policy (and -project) threads.
jdub
High	Approved	example-content	jdub	No update given.
kamion
Essential	Approved	ue-partitioning-tool	kamion	Not started; will start next week once Flight CD 1 is done.
Essential	Approved	ubuntu-express-base-system	kamion	Not started; will start next week once Flight CD 1 is done.
Essential	Approved	ubuntu-express-copy-filesystem	kamion	Not started; will start next week once Flight CD 1 is done.
Essential	Approved	ubuntu-express-bootloader	kamion	Not started; will start next week once Flight CD 1 is done.
Essential	Pending Approval	ue-gnome-ui	kamion	Not started; will start next week once Flight CD 1 is done.
Essential	Approved	ue-language-packs	kamion	Not started; will start next week once Flight CD 1 is done.
Medium	Approved	cd-build-process	kamion	jigdo improvements done, yielding the vast bulk of the wins here; elmo reckons parallelisation will be a loss with little's current hardware ("I/O bandwidth of a straw"); single-architecture rebuilds not started, but not blocked.
Medium	Approved	cd-bootloader	kamion	syslinux 3 merge partly done, but blocked on finishing Flight CD 1 for general sanity reasons. gfxboot work blocked on that. CD timeout work not started.
General		General	kamion	misc: insane pile of merges, lots of uninstallable-fixing, seed reorganisation, etc. Assuming I get Flight CD 1 done this week, I intend to spend next week on (a) the big apt-setup merge from Debian (fixing lots of bugs) and (b) Ubuntu Express.
Meeting:				Further meeting between kamion and mdz to discuss Merges, CD Blockers, Kubuntu CD builds (with Riddel) and Syncs (with James)
keybuk
High	Approved	hardware-activation	keybuk	firmware moved to /lib/firmware as new standard path, kernel-wedge updated, BenC to update kernel-source
High	Approved	udev-roadmap	keybuk	udev-roadmap: klibc updated, but decided not to use it for udev. modutils now up to date and owns the isapnp aliases and blacklists; potential issue with installer/initramfs modprobe (busybox) not supporting blacklists. udev packaging is progressing well; chose intersection of Debian and SuSE rules for our own, still need to sort out upgrades. Status of the new coldplugging infrastructure... prototype tested yesterday and seems to work, need to code up a full version and update initramfs -- ~1 day
High	Approved	network-magic	keybuk	NetworkManager doesn't work with Atheros cards, which are pretty common in the target userbase. Perhaps this should be deferred until the cards can be supported (which is most likely when we have an open driver for them as iz driver bug)
High	Approved	hardware-detection	keybuk	?? No update given
Medium	Braindump	streamlined-boot	keybuk	bootchart packages made available, s shaved by removal of boot-time depmod. Next up see what the udev changes do, then fix readahead. Kamion noted that: installer issue is no longer relevant for now because I switched d-i to module-init-tools. Note from mdz: streamlined-boot also has a list of things to remove from the boot process...?
Meeting:				Further meeting between keybuk and mdz to discuss NetworkManager, udev, boot process
krstic
Proposed	Pending Approval	community-server-hardware-testing	krstic	No update given.
mdz
Essential	Approved	dapper-release-process	mdz	No update given.
High	Approved	simplified-livecd	mdz	No update given.
Meeting:				Additional meeting with James re SysAdmin stuff, And James H re: macquarie, little
mvo
High	Approved	release-upgrades	mvo	Not yet started. To be prioritised based on time estimates for all goals next week.
Medium	Braindump	default-apt-sources	mvo	?? No update given
General		General	mvo	This week: * automatic removal of dependencies: - merged work from UBZ with mainline, want to bounty dburrows. * support 3rd party package - support for sources.list.d added to apt/synaptic - gdebi (direct installing of debs) makes progress. Will do: * support 3rd party packages channels and work on a gui for that (releated to "better repo dialog" spec) * unattended package upgrades checking script * gdebi upload to universe pitti : can I have you for hide-admin-tools next week? for the u-n side? (should be a small change) / pitti: sure, that should be possible.
ogra
High	Drafting	thinclient-faster-startup	ogra	* made all the changes we worked out at ubz * did some bootcharting * enabled usplash, to recognize we loose 5sec through it :/
Medium	Drafting	thin-client-memory-usage	ogra	* did some further testing * played with module blacklisting etc * talked to daniels about reducing the color palette by default to 16bit for thin clients
General		General	ogra	== thin-client-sound == * proof of concept works fine here (there is way less to do than the spec says, will correct this) * implementation and coding will take another day. == thin-client-local-devices == * not started yet * ltspfs packaged but not yet uploaded (needs more testing). == gnome-screensaver (generally) == * started to adopt the .desktop file scheme for gnome-screensaver in xscreensaver * split the hacks into 4 packages for shipped/non-shipped, gl/non-gl (per sabdfl request) == gnome-screensaver-default-image == * not started yet == planned for the week == * finish up my local bzr archive of ltsp mainline make it public and add my changes after cross-check through mdz * get the specs texts finished and finally approved * further ltsp testing in all areas * finishing xscreensaver stuff * making the first edubuntu CD, getting familiar with liveCD builds (we had none last release)
Meeting:				Further meeting between ogra, mdz and JaneW to discuss edubuntu and edubuntu specs re: thin-client-local-devices, ltsp bzr transition, everything.
pitti
Medium	Approved	automatic-printer-conf	pitti	automatic-printer-conf: Plan: upgrade to latest cupsys beta; ETA: 6 hours (big package, lots of Ubuntu changes)
Medium	Approved	gstreamer-audio-backend	pitti	gstreamer-audio-backend: Blocks: I need gstreamer 0. beta in dapper; Plan: upgrade ALSA libs to 1. and make necessary adjustments according to spec; Time estimate: 1 day ALSA, 2 days gstreamer; libgnome: unclear
General		General	pitti	hide-admin-tools-to-users: implemented backend part of hide-admin-tools-to-users; Plan: coordinate with seb128 and mvo about updating all desktop files and gnome-menu/update-notifier Time estimate: 2 mandays. rosetta-firefox-support: Blocks: carlos currently plays with moz2po to actually get it working; ETA unknown. general for next week: finish merges, catch up with security, clean up anastacia
seb128
Essential	Approved	dapper-desktop-plan	seb128	Packaged GNOME 2.13.2 (with dholbach)
High	Approved	menus-revised	seb128	Started menus-revisited changes, to be pushed to implemented next week.
General		General	seb128	Planned for next week: gconf transition (package split, location of the default change, new format to store custom defaults), Note: gstreamer 0. due in first week of Dec.
sivan
Medium	Approved	home-user-backup	sivan	No update given.
Mithrandir
Medium	Approved	live-cd-performance	tfheen
Medium	Approved	livecd-unionfs	tfheen
General		General	Mithrandir	This week: - merges - making it possible to build cdebconf widgets out-of tree. Next week: - merges - help making the CDs installable again so I can implement some of my CD-based specs and start doing the live cd boot speed instrumentation. Blocked on: - generally bugzilla being utterly slow due, mMakes it hard to know when bug triage and merges are possible to do. To prioritise: CD and livefs installability to help Colin in preparing the first Flight, to coordinate with Colin regarding what needs to be done.
pitti
General		General	pitti	hide-admin-tools-to-users: implemented backend part of hide-admin-tools-to-users; Plan: coordinate with seb128 and mvo about updating all desktop files and gnome-menu/update-notifier Time estimate: 2 mandays, gstreamer-audio-backend: Blocks: I need gstreamer 0. beta in dapper; Plan: upgrade ALSA libs to 1. and make necessary adjustments according to spec; Time estimate: 1 day ALSA, 2 days gstreamer; libgnome: unclear. automatic-printer-conf: Plan: upgrade to latest cupsys beta; ETA: 6 hours (big package, lots of Ubuntu changes) rosetta-firefox-support: Blocks: carlos currently plays with moz2po to actually get it working; ETA unknown general for next week: finish merges, catch up with security, clean up anastaciark.
fabbione
General		General	fabbione	Progress on ubuntu-server (https://wiki.ubuntu.com/ServerCandy): Community involment:- #ubuntu-server created- waiting jdub to create mailing list- ubuntu-instant parallel project started from the community to add value to -server (~ server for dummies)+ Implementation:- Create an MD5 checker for the Ubuntu Installer rescue mode (see specs): server side code is done and tested. rt request filed for datacenter integration. * During this week:- kernel security (big mess + ABI change)- need to review policy for security with ABI changes (lrm and linux-meta) * Next week: - kernel security left overs (if any) - merges- ubuntu -server and ubuntu-cluster work.
Meeting:				Further meeting between mdz, fabbione and JaneW to discuss goals for Dapper cycle.
Riddell
General		General	Riddell	This week: (kubuntu-roadmap-dapper) packaging KDE 3.5, preparing for the libstdc++ transition and discussing it with the Debian packagers, (kubuntu-translations) preparing KDE packages for rosetta, and doing the artwork for Kubuntu breezy CDs. Also tidied the Kubuntu wiki pages, (kubuntu-documentation) preparing documentation for breezy and preparing KubuntuDapperPackagerManager for Bounty. Next week, doing c++ transition, simplify-kde, documentation packaging, hopefully kubuntu-system-tools fixing knetworkconf kubuntu-system-tools is still drafting, needs to get it polished up before starting the implementation – to be done this week. Also over the next week Riddel to take charge of getting kubuntu CD builds going again (uninstallables, livefs builds, etc.), has been waiting for c++ transition for this.
daniels
General		General	daniels	daniels completed: x11r7 rc1 and assorted bugfix fun. a few merges, syncs. prepared xorg breezy-update. debugging mcpp. / daniels wip: x11r7 rc2 tarball updates (~0 new tarballs). everything but server done; server and drivers are in local testing as there's no point uploading (see below). / daniels blocked: glibc for building xorg-server. jbailey and I developed patch to fix. new binutils upstream needed to let glibc build so xorg-server can build so the drivers can build. bugzilla. / daniels planned: finish x11r7 rc2 tarballs. start work on uninstallables. update mesa to new upstream when it comes. / daniels x-roadmap: permanently wip by definition. eta: jan 20th. dbus-restarts: largely fixed (we don't restart dbus anymore). mostly informational for upstream use. eta: not planned. gdm-keyboard-layout: superseded by a few other specs which don't involve me. eta: no idea. faster-gnome-startup: some mcpp issues to iron out which have been causing me pain today. eta: unsure (else only gnome work left). / doko fabbione, Znarl did tell me it was long term, but it looks like we need it short term, or at least have separate i386 and amd64 machines / mdz daniels: so r7 final is expected in Jan?
Meeting:				Further meeting between daniles and mdz re.binutils/glibc/xserver-xorg
dholbach
High	Drafting	power-management-configuration	desrt/ dholbach?	power-management-configuration: desrt, mjg59, pitti and hughsie are currently in the loop. the biggest problem is that gnome-power-manager/hal upstream want to have hal running as root, whereas pitti ... doesnt want to. We already considered not using g-p-m and rely on the scripts, Matthew didn't like that. desrt started hacking on various things for testing reasons, but unfortunately there was no agreement made yet.
General		General	dholbach	This week: done: big heap of merges, gnome 2.13.2, bug triage, missing merges, ubuntu-docs packaging. Next week: bug triage, missing merges, desktop team organisation, bug day, talking accessibility with hno73, c++ allocator change, inclusion-of-docs: started to try to understand 80M of docs and how they are built; no upload yet, since there were no big changes yet. acessibility-*: need to catch up with hno73, since the BOFs were not scheduled in Montreal.
Meeting:				Additional meeting withdholbach and mdz re. power-management-configuration, inclusion-of-docs
General:
General		General	All	pitti asked that some more people be able to sync packages, as it costs a lot of time to track these issues for several days, and they block other packages often. The request is that they can carry out the actual sync in katie. Currently: elmo, mdz and kamion can do this. It can cause conflicts when more than one person is synching through... Mithrandir suggested using the wiki or bugzilla or something sounds like a good plan, IMO. / Pitti: when we discover that something can be synced, we should do it right away otherwise new changes interfere with that, etc. We already had that case. Also noted that locks should be announced in #u-d, as there has been a little double-work due to people not announcing what they're doing.
Meeting:				Additional meeting with elmo, mdz and kamion to discuss synching