## Dapper Status 1 Dec 2005
Priorities	Status Indicators:	Goal Type	Expectation
Essential	DONE	Confirmed Dapper goal	Certain
High	On track, all OK	Considered Dapper Goal	Probable
Medium	Behind schedule, but will catch up	Not guaranteed for Dapper	Unlikely
Low	Blocked or needs management input		Deferred

Prio.	Stat.	Name	Assign	Days	Dapper Development Status Update: 1 December 2005
BenC
High	Pending Approval	testing-server-hardware	ben-collins	10	To follow after 2.6.15 is completely installed and buildable.
Medium	Pending Approval	ubuntu-server-kernel	ben-collins	1	To follow after 2.6.15 is completely installed and buildable.
Medium	Approved	preventing-hardware-support-regr...	ben-collins	3	To follow after 2.6.15 is completely installed and buildable.
General		General	BenC		* DONE: Get 2.6.15 as main kernel (this has been the bulk of my work) / * specs done: initramfs-updates, implemented kernel side to use update-initramfs script / * specs dependent on 2.6.15 kernel: ubuntu-server-kernel, testing-server-hardware, preventing-hardware-regressions, udev-roadmap / * goals for next week: ubuntu-server-kernel, and start of preventing-hardware-regressions framework, complete merges, kernel-wedge and kernel-package.
Meeting:					None required.
daniels
High	Approved	x-roadmap	daniels	35	?? No update given Not present.
General		General	daniels		On leave. / blocked: nothing anymore.
Meeting:					None listed.
dholbach
High	Approved	power-management-configuration	dholbach ? To be reassigned to mjg59?		Added explanations about the NEW approach, that mjg59, pitti and desrt agreed on, asked pitti and mjg59 to have a look, didn't contact hughsie yet, although he made some notes on the wiki page
High	Approved	best-practices-bugs	dholbach		Added some notes to the Bugs/ pages, community tested them on the last Bug Day and they seem to have "worked", basically done now.
High	Approved	test-plans	dholbach		No update given.
Low	Approved	inclusion-of-docs	dholbach		Fixed a couple of bugs with mdke, uploaded the new version, will continue with uploading new versions twice a week, mdke agreed on making the community aware of possibilities in doc proofreading/checking/participating
General		General	dholbach		* a11y-*: apart from the meeting and the new mailing list (thanks jeff), no progress :-( / * this week: huge amounts of bug triage, community stuff (desktop team, motu), std allocator change / * next week: more bug triage (we will get bugzilla clean next week :)), organise a motu review day, tackle DesktopTeam/TODO, more merges? investigate with slomo a bit more on formal-test-plans.
Meeting:					None listed.
doko
High	Approved	openoffice-gnome	doko		Started merging / updating to version 2.0.1.
Medium	Approved	toolchain-roadmap	doko		gcc updates (3.4.5 final, 4.0 in a state allowing KDE to build on hppa), amd64-biarch blocked by glibc
Medium	Approved	python-roadmap	doko		Python merges, started python-central update
Low	Pending Approval	java-roadmap	doko		Merges done by charles, two left.
General		General	doko		next week: / - toolchain-roadmap: amd64-biarch, when ready / - python-roadmap: python-central, start converting packages in main, get rid of python2.3 (start it ...) / - openoffice.org: try to build a first package. feedback for gnome-integration needed
Meeting:					None required.
fabbione
High	Approved	server-candy	ubuntu-server	30	Progressing: MD5 checker core is ready (both server and client side). Client frontends need to be done. other stuff is waiting to complete the MD5 task. Community is growing slowly still waiting for jdub to make the mailing list, otherwise no / progress since last week.
Medium	Approved	probe-for-root-filesystem	fabbione	10	BLOCKED, mainly by the new udev stuff, which blocks the boot-time side and testing. Note: it's hard to test d-i changes correctly when the installed system doesn't work right. I don't like blind modifications if i can avoid them is better
Medium	Approved	boot-from-usb	fabbione	5	BLOCKED, by prode-for-root-filesystem, and testing.
Medium	Implemented	installer-volume-management	fabbione	2	Implemented. There is one (minor corner case) bug that is giving me headacke to fix. Otherwise it ROCKS.
Medium	Approved	ubuntu-cluster	fabbione	15	Made local packages of new ocfs2 tools. need testing.
General		General	fabbione		* last week: done with my merging, one (zlib) is stalled on libc6-i386-dev | ia32-libs-dev. / * next week: try to kill the last installer-volume-management bug, cluster love to the tools we already have and server-candy full speed.
Meeting:					None listed.
infinity
High	Approved	reducing-duplication	adconrad		Ongoing effort, as always, this last week saw good progress on kicking out multiple versions of libdb
Medium	Drafting	usplash-initramfs	adconrad	2	Tested vga16fb changes to use a lower resolution, muddled with assembly in syslinux to make the same change for CD booting, need more testing. Scott has released his lock on initramfs, so all of these things will head into full-tilt next week. Expect to see progress on all but (maybe) thin client usplash this week.
Medium	Approved	splash-down	adconrad	7	Have a reasonable working implementation, will need to ping maintainers of display managers to hook things in correctly and coordinate uploads
Medium	Implemented	initramfs-updates	adconrad	2	Done.
Low	Braindump	thinclient-usplash	adconrad	4	Scheduled for week after next. - ogra, talk to me about this, the spec itself doesn't even exist yet, and we should draft one.
General		General	infinity		* last week: lost of work on linux-restricted-modules updating / fixing, and getting to work with new kernels; sorting patches for a big PHP security rollup (nothing big about the individual bugs, just that we have enough piled up to do a bit release now); general buildd, merge, and bugfix work. / * my outstanding merges: portmap was taken by Mithrandir, initramfs-tools is currently heavily forked from Debian, and may not be "merged", so much as cherry-picked to and from, mozilla-thunderbird is waiting on my talking with the Debian maintainer about packaging Tbird 1.5 ASAP, php5 will be re-merged with the set of security uploads mentioned above, enigmail is waiting on the thunderbird 1.5 decision. Feel free to fire up MOM again, as those (except portmap) are all (in my mind) false positives for "outstanding". :) / Note from ogra: what should we spec about usplash on thin clients ? its only turning on the splash flag on the kernel commandline - no special needs. It has been working for 2 weeks. Had timeout probs that were solved with new initramfs.
Meeting:					Further meeting between infinity and kamion to discuss l-r-m and installer, meeting between infinity and ogra required for thin-client usplash.
iwj/Diziet
High	Approved	automated-testing	ijackson	10	Discussion in debian-* seems to have finished. Have spoken to Robert Collins about wider testing arrangements and am waiting for a straw man design idea from him. *BLOCKED* on Robert. I hope to start implementation next week.
High	Approved	default-applications-firefox	ijackson	10	Have applied (without trouble) patches from RH to make Firefox use Gnome MIME handling, but these only solve (a fairly small) part of Firefox's MIME problems. Work will have to continue. I am currently constructing another interim Firefox release for Dapper development to help with issues found so far.
Medium	Approved	developer-documentation	ijackson	15	Not started, not blocked.
Medium	Drafting	thinclient-local-devices	ijackson / ogra ?	10	Spec is still in Drafting. *BLOCKED*
Low	Drafting	package-dependency-fix	ijackson	10	Not yet started .
General		General	iwj		Launchpad Client Certs (https://wiki.launchpad.canonical.com/SSLCertificateAuthentication): Proof of concept successful and written up on wiki (with full instructions, example config, etc.). Nothing more to do from my end (hopefully) except support Launchpad people with development and deployment. / Firefox maintenance: See above. The current package has several problems. I'm aiming for a new release on Friday (tomorrow) which will have fixes for whatever I can get done by then. / Others: no more ancient 7.07 gs-esp horror; not seen many problems with gs-gpl and gs-esp 8.15; yay. Merged mozilla (security fix), no problem. / The RH patch is relatively sane and I'm happy to carry it. So we'll definitely get at least that far. / I might try to tart it up to make it a #ifdef for upstream. / It'll use the Gnome ones _most of the time_ but it's still on crack. / Note from mdz: we'll do the best we can with it; if there's a lot of code to be written, it may not be feasible for us, automated testing would take precedence in that case
Meeting:					None required.
jbailey
General		General	jbailey		* LocalesThatDontSuck: glibc parts done. Need to figure out best way to handle locales bug reports. My guess is forward them to Danis Barbier for now and coordinate a merge monthly or so with pitti. / * ToolchainRoadmap: Recovered from last weeks breakage, glibc built everywhere now. libc6-i386 coming next week for amd64. LaMont to get back to me whether ia64 wants it, or if they're dropping i386 support. / * Other: Need to go through bugzilla and punt anything that's not glibc or lkh related to other people. / * glibc merge will come after all the changes that we're doing. The changes are blocking other people, the merge isn't.
Meeting:					None required.
jdub
High	Approved	example-content	jdub		No update given not present. Have mailed jdub for a status update.
Meeting:					None required.
kamion
Essential	Informational	ubuntu-express	kamion		Informational overview spec.
Essential	Approved	ue-partitioning-tool	kamion		Finished and uploaded first cut at partman.deb, which shockingly seems to almost work if you know how to drive it.
Essential	Approved	ubuntu-express-base-system	kamion		niemeyer and I sorted out last week's svn2bzr bug, so I nearly have a working import; just waiting for Guadalinex to actually make their dump sufficiently up-to-date now (pinged them again today). No other progress.
Essential	Approved	ubuntu-express-copy-filesystem	kamion	3	niemeyer and I sorted out last week's svn2bzr bug, so I nearly have a working import; just waiting for Guadalinex to actually make their dump sufficiently up-to-date now (pinged them again today). No other progress.
Essential	Approved	ubuntu-express-bootloader	kamion		niemeyer and I sorted out last week's svn2bzr bug, so I nearly have a working import; just waiting for Guadalinex to actually make their dump sufficiently up-to-date now (pinged them again today). No other progress.
Essential	Approved	ue-gnome-ui	kamion		No other progress. Semi-blocked on an svn2bzr bug that prevents me from importing the Guadalinex repository (sent to niemeyer).
Essential	Approved	ue-language-packs	kamion		No other progress. Semi-blocked on an svn2bzr bug that prevents me from importing the Guadalinex repository (sent to niemeyer).
Medium	Approved	cd-build-process	kamion	2	No progress (nothing urgent left here).
Medium	Approved	cd-bootloader	kamion	5	Reviewed gfxboot patch; found it hideous and infeasible to port to 3.11 myself. Talked to SuSE folks about getting a gfxboot patch for syslinux 3.11; I have this in my hands now and it's much better and doesn't break text mode at least, but I haven't quite had time to set up a graphical mode yet.
General		General	kamion		misc: Finished my merges. Lots of work on the big move to 2.6.15, which has consumed a big fraction of my time this week. I have a working installer nearly ready to go now; the live CD will take a little longer to get working again since we're now using initramfs in d-i. Minor bug-fixes to pcmciautils, which I packaged week-before-last. / next-week: Finish move of installer and live CD to 2.6.15; upload gfxboot and get it enabled by default; try to glue debconffilter onto the front of partman (this is pretty much a torture test of whether our UE implementation plans will work); prod Guadalinex until we can finally get the UE bzr import done and move on; archive-copier changes for language-pack-vs-support. With any luck, Flight CD 2 next Thursday or so.
Meeting:					Further meeting between kamion and mdz to discuss Merges, and Syncs (with James/elmo), and Simplified LiveCD with Mithrandir.
keybuk
High	Approved	hardware-activation	keybuk		Beginning, alsa, hdparm and networking to become udev events; ntpdate to become if-up.d script. those are the most tested and easy to do.
High	Approved	udev-roadmap	keybuk	14	Done, uploaded, the big bugs shaken out.
High	Approved	network-magic	keybuk	20	No progress, discovered it doesn't seem to bring up wifi interfaces until a user logs in. blocked on glibc dns patch. might not be doable anyway.
High	Informational	hardware-detection	keybuk		Note that this is an informational specification, it describes in detail what we're going to do from a high vantage point -- the actual "implementation" spec is udev-roadmap.
Medium	Braindump	streamlined-boot	keybuk	10	Planned on my whiteboard, need to dump onto wiki. mostly moving rcS stuff about a bit and removing some extraneous messages
General		General	keybuk		misc: one merge remaining (sysvinit, to be done with streamlined-boot). dpkg conffile handling still to fix.
Meeting:					Further meeting between keybuk and mdz to discuss NetworkManager, udev, boot process
krstic
Proposed	Pending Approval	community-server-hardware-testing	krstic		No update given. Not present.
Meeting:					None required.
lathiat
High	Drafting	zeroconf	lathiat		No update given. Not present.
Meeting:					None required.
mdz
Essential	Approved	dapper-release-process	mdz		No update given.
High	Approved	simplified-livecd	mdz		No update given. - may be reassigned to Mithrandir – to be confirmed.
Meeting:					Additional meeting with James re SysAdmin stuff, And James H re: macquarie, little.
Mithrandir
High	Approved	media-integrity-check	tfheen	2	Blocked by Syslinux, in the archive, waiting for syslinux boot menu resolution, but looking good. Might need some template adjustments.
High	Approved	network-authentication	tfheen	30	No progress, I've been thinking about how to do it, but nothing solid yet.
Medium	Approved	live-cd-performance	tfheen		Bootchart-udeb uploaded, main inclusion report is written and review asked for, will add to d-i lists once it's in main. Need to investigate size of bootchart + deps for live seed, we might want that in.
Medium	Approved	livecd-unionfs	tfheen	1	No progress (livecd-unionfs is approximately blocked on simplified-livecd)
Medium	Approved	one-true-path	tfheen	3	No progress
Medium	Approved	openoffice-amd64	tfheen		No progress
Low	Braindump	livecd-squashfs	tfheen		No update given. Not a priority.
General		General	Mithrandir		This week: a lot of faff and merges, got dragged into a bunch of d-i stuff when some kbd-chooser breakage was discovered and I spent time cleaning that up, live-cd-performance and media-integrity-check are both looking good and approximately on schedule. / Next week: some vacation, Fix up the d-i stuff I've been working on (kbd-chooser). Look at getting one-true-path implemented. / Blocked on: media-integrity-check blocked on syslinux menu, but apart from that, nothing. livecd-unionfs is approximately blocked on simplified-livecd.
Meeting:					Further discussion required with Colin Watson re syslinux, and discussion with kamion and mdz to discuss simplified-livecd.
mvo
High	Approved	release-upgrades	mvo	7	Not yet started. To be prioritized based on time estimates for all goals next week.
High	Approved	third-party-packages	mvo	7	Did: gdebi (direct deb install tool) almost ready for upload into archive (needs new python-apt first) [Support for packages by third parties in external repos]
Medium	Braindump	default-apt-sources	mvo		* tried to make apt more smart about failed network sources [Default apt sources.list configuration]-> might be used for [Improved handling of APT cdrom: sources as well
General		General	mvo		* the usual dance of mail/bug triage/irc / * upload new apt/python-apt/gdebi + all depenencies (apt abi break) / * gdebi is in the archive, that means one bit of the 3rdPartyPackages spec is implemented (still needs testing) [Support for packages by third parties in external repos] / * build a package for unattended-upgrades script, not yet integrated into the APT::Periodic system [Unattended package upgrades] / * started with the dist-upgrade tool, extended/cleaned up update-manager (u-m is responsible for detecting new releases and downloading the actual script) it detects new releases now, can download/display release notes and download/extract the upgrade script tarball (+ cleaning up afterwards). / * some more bits of python-apt supported where needed for the update-manager changes / * cmd-not-found magic work with zyga, we have a package now for it, a (small) patch for bash was submited to make integration smoother / * changed language selector to implement the LanguagePackVsSupport spec (together with pitti) / * update-notifier does not start when there is a admin group on the system but the user is not part of it, implemented my parts of the HideAdminTools spec [HideAdminTools] / Will do: / * more work on the dist-upgrade tool, the actual dist-upgrade code comes next / * 3rd party packages channel work / * integrate unattended upgrades script into the APT::Periodic system
Meeting:					None required.
ogra
High	Drafting	thinclient-faster-startup	ogra		Mainly bug hunting in the new initramfs, works fine now, thanks Keybuk, spec pending.
Medium	Pending Approval	thin-client-memory-usage	ogra	5	Was waiting for the new initramfs/udev/kernel architecture for modlue blacklist testing, spec pending.
Medium	Pending Approval	thinclient-sound	ogra / jam	2	Initscript for the client side and package work done locally, spec pending.
Medium	Drafting	thinclient-local-devices	ijackson / ogra ?		No further work yet, spec still in drafting.
Medium	Drafting	screen-saver	ogra		No update given. All issues around transition from xscreensaver to gnome-screensaver must be considered.
Medium	Approved	screensaver-default-image	ogra		No further work done yet, package ready so far, need images.
General		General	ogra		* general: waved in the multiarch-client patch and uploaded bzr branch for mdz inspection. gobby main inclusion report for edubuntu done (looks like we'll get gobby 0.3.0 exclusively for ubuntu according to pkern (upstream and DD)). / last weeks goals: requested changes to ldm done and sent to mdz, thin-client sound initscript done, packge data for ltsp-sound (changes to control and rules file) added (locally not yet online) in bzr, etherboot: mknbi seems not to produce usable images (only tested with breezy yet) needs further investigation (also with the new kernel), liveCD filesystem prepared but waits for ubuntu-desktop/edubuntu-desktop being installable, xscreensaver merge / done, selected hacks in xscreensaver-data are working with gnome-screensaver now. mailed gnome-screensaver upstream (will provide a patch for lockscreen), edubuntu ready for flight2 (considering to drop kino from the desktop since video on ltsp clients sucks), all merge bugs done o far, will propose to drop gtk-qt-engines its not supportable for 3 years, upstream works very slow and doesnt fix bugs (not even the ones with patches) it seems, gnome / -screensaver not in main yet, will wait until after flight 2 and for (#3044). / * next weeks goals: find out the bugs and fix the Xorg autodetection on thin clients, finish the ltsp sound stuff, fix what mdz sends back to me of my ldm/multiarch stuff, do the xscreensaver hack split for #3044, finally get gnome-screnesaver to main, inspect the mknbi/etherboot problem, get the liveCD ready and test edubuntu fledgling1 (dapper flight 2) live and install, start working on hwdb-client changes, inspect changes that have to be done / to edubuntu-artwork for dapper. / Note from kamion: (alpha CD branding for derivatives typically tracks the real one to avoid hideous confusion on cdimage, so I'd prefer "Edubuntu Flight CD 2")
Meeting:					Further meeting between ogra,mdz, sbalneav to discuss local devices – may not make it for dapper, and a meeting between ogra, mdz and JaneW to discuss edubuntu and edubuntu specs re: thin-client-local-devices, ltsp bzr transition, everything.
pitti
High	Implemented	belocs-locales	pitti	2	Reassigned to pitti from BenC. Implemented. DONE: fully implemented, new glibc, locales, and langpacks are in the archive.
Medium	Approved	automatic-printer-conf	pitti	2	PLAN: much harder than expected in the spec, start upstream discussion about hal support and detecting unconfigured printers
Medium	Approved	gstreamer-audio-backend	pitti	3	BLOCK: gstreamer 0.10 for creating the alsadmixsink
Medium	Approved	language-pack-vs-support	pitti		DONE: mvo implemented langselector changes; PLAN: installer needs string change, then it's complete (something for Kamion, bug is filed)
Medium	Approved	langpacks-desktopfiles	pitti	5	Nothing done, no time; PLAN: zyga has some patches, apply and test them; if performance regressions are negigible, upload, else this requires further discussion
Medium	Approved	firewall	pitti		carstenh proposed bounty; no coding from my side, just review; no plans
Low	Pending Approval	automated-problem-reports	pitti	15	DEFERRED. BLOCK: approval from Keybuk, would appreciate opinions from other people, too (elmo, Kamion, mdz) since this is very intrusive.
General		General	pitti		Reducing-duplication: DONE: db4.1, krb4, are in universe, ucs-snmp about to go (if the hppa buildd condescends to build cyrus21-imapd); checked db4.2 removal, it's hard / merges: DONE: non-blocked merges are finished, remaining ones are stalled by external reasons; BLOCK: tbird l10n packages for tbird 1.5, cdrecord for upstream version regression / rosetta-firefox-support, pmount-uber-alles, firewall: no change since last week / plan for tomorrow: catch up with the huge amount of main inclusion reports, people start killing me about them / Note from mdz: decision has been taken to defer automated-problem-reports. if there is a third party interested in working on it as a bounty, great, otherwise it's too much. The spec should still get approved to allow for it to be bountied.
Meeting:					None required – maybe discuss automated-problem-report spec approval with mdz.
seb128
Essential	Approved	dapper-desktop-plan	seb128	10	Started to look on changes, spoke with desktop team/upstream about some of them.
High	Approved	hide-admin-tools-to-users	seb128	2	DONE: design decision was taken, sudo changes reverted; discussed further actions with seb128, who will now do/coordinate the rest. Reassigned from pitti.
High	Approved	menus-revised	seb128	2	No update this week (todo: oo.o2 to upload)
High	Approved	video-playback	seb128	5	No update this week (still waiting for gst0.10)
Medium	Approved	faster-gnome-startup	seb128	3	gconf transition is done/ok – should be finished in next week.
Medium	Approved	rhythmbox-ipod	seb128	5	Fixed libgpod according to pitti's comments, got it promoted, updated rhythmbox to the new 0.9.2 using it
General		General	seb128		misc: desktop bug triage, syncs, fixed GNOME packages for firefox1.5, some new GNOME updates/sync with Debian / next week: dapper-desktop plan, continue the desktop bug triage
Meeting:					None required.
sivan
Medium	Approved	home-user-backup	sivan	10	No update given. Will this be pursued for Dapper? mdz to respond.
Meeting:					None required.
Riddell
High	Approved	kubuntu-roadmap-dapper	jr	80	Packaging KDE 3.5, some modules blocked on subversion upload
High	Drafting	kubuntu-express	jr	25	Riddell and jjesse are jointly responsibly for driving this spec to completion.
Medium	Approved	kubuntu-documentation	jr	10	Settings up documentation for dapper to work properly with KDE, dholbach has offered to help with the docs stuff – buildsystem-wise
Medium	Pending Review	kubuntu-system-tools	jr	10	No update given.
Medium	Approved	kubuntu-package-manager	jr	20	No update given.
Proposed	Braindump	kubuntu-launchpad-integration	jr	3	No update given.
General		General	Riddell		KDE 3.5 packaging and merges and libstdc++ transition and rosetta support / next week, finishing all that off especially merges, update seeds, simplify-kde, also moving kubuntu-express to review seems to have slipped my mind so I'll make sure to remember that / Note from mdz: you have ~16 outstanding merges, need to get those completed ASAP, there are also unresolved kubuntu-related anastacia items, and remember to merge ubuntu->kubuntu seeds / libarts1-akode | 4:3.5-rc2-0ubuntu1 | dapper | amd64, i386, ia64, powerpc / please follow up and see what's happening with it.
Meeting:					None required.
General:
General		General Comments	All		* If changes to assignee, statuses and priorities are made to the specs in LP affected parties must be notified by e-mail or IRC ping. / * Check your Priorities, Statuses, Estimated Developer Days and Expectation of Delivery in LP and keep them up to date. / * Remember to mention if actions listed here one week, such as discussions etc, have been completed the next week. / * Note if a further discussion needs to take place on any item, and who need to be present. / * MERGES to be completed ASAP - please everyone push merges to completion.
Meeting:					No additional group meetings required this week.